## Time Log
Date | Hours | Activity ID | Comments
2016-06-09 | 1 | 1
2016-06-13 | 2 | 1
2016-06-18 | 2 | 1
2016-06-18 | 1 | 1 | Set Up GitHub
2016-06-18 | 0.5 | 2
2016-06-19 | 0.5 | 8 | Intro Paragraph
2016-06-19 | 0.5 | 8 | Motivation and start terms
2016-06-19 | 1 | 19 | Look at raspberry pi's and supported languages
2016-06-20 | 1 | 20 | Researched web servers and API's
2016-06-20 | 0.5 | 8 | Chose terms, formated definitions, made refrences
2016-06-20 | 0.5 | 8 | Finished defining terms
2016-06-21 | 0.5 | 9 | Created figure and did overview intro paragraph
2016-06-25 | 1 | 9 | Create system context diagram and write supporting paragraph
2016-06-25 | 0.5 | 10 | Started Use Case Diagram
2016-06-25 | 1.5 | 10 | Finished use case diagram and set up use case sections
2016-06-26 | 1 | 10 | Finish Use Case details
2016-06-26 | 0.5 | 11 | Finishe last sections of Vision document
2016-06-27 | 0.5 | 3 | Finished project plan setup
2016-06-27 | 0.5 | 12 | Finish Intro
2016-06-27 | 1 | 18 | Finished most of gantt chart, still needs review of details
2016-07-02 | 0.5 | 18 | Finalize Gantt chart and put in document
2016-07-02 | 1.5 | 13 | Finished WBS section
2016-07-02 | 0.5 | 14 | Researched COCOMO
2016-07-03 | 1 | 14 | Finished Cost estimate
2016-07-03 | 0.5 | 15 | Finished elab plan
2016-07-03 | 0.5 | 4 | Set up SQA document
2016-07-07 | 1 | 19 | Set up Raspberry PI
2016-07-09 | 1.5 | 16 | Finished document
2016-07-12 | 0.5 | 7 | Set up environements and started projects
2016-07-12 | 0.5 | 21 | Started Receiver
2016-07-12 | 0.5 | 22 | Started Sender
2016-07-14 | 0.5 | 21
2016-07-14 | 0.5 | 22
2016-07-23 | 1 | 21
2016-07-23 | 1 | 22
2016-07-24 | 2 | 23
2016-07-26 | 2 | 24
2016-07-31 | 1.5 | 26 | Set up encryption classes
2016-08-13 | 2 | 26 | Set up sign/verify in java
2016-08-22 | 1 | 30 | Evaluated schedule/made adjustments
2016-08-28 | 1 | 5 | Make presentation
2016-08-30 | 1 | 27 | Play with encryption
2016-08-31 | 2 | 27 | Final encryption tweaks for demo
2016-09-01 | 1 | 6
2016-09-01 | 1 | 25
2016-09-05 | 0.5 | 31 | Email about feedback
2016-09-13 | 0.5 | 32 | Review Possilbe Revisions
2016-09-13 | 1 | 42 | Set up and look at Use
2016-09-18 | 1 | 43 | Working on Classes
2016-09-19 | 0.5 | 43 | Finishing up classes
2016-09-19 | 0.5 | 44 | Finish Associations
2016-09-19 | 0.5 | 33 | Decide on Constraints
2016-09-20 | 1 | 33 | Finish Constraints
2016-09-20 | 0.5 | 45 | Set up document
2016-09-24 | 0.25 | 50
2016-09-24 | 1.5 | 46 | Finished component diagram and interface specification
2016-09-25 | 1 | 46 | Finish section 2
2016-09-25 | 1 | 47
2016-10-03 | 2 | 48 | Finish Document
2016-10-03 | 0.5 | 35 | Review Test plan document structure
2016-10-04 | 0.5 | 51 | Finish Set UP
2016-10-10 | 1.5 | 52 | Finish sections 1-8
2016-10-11 | 1 | 53 | Finished document
2016-10-16 | 0.25 | 54 | Finished document set up
2016-10-16 | 0.5 | 55 | Finish Document
2016-10-18 | 0.25 | 56 | Finished setup/prep
2016-10-18 | 1.5 | 57 | Creating Presentation
2016-10-21 | 2 | 38 | Studied up on classes and modules, build user classes
2016-10-22 | 2 | 38 | Setting up console control flow
2016-10-23 | 6 | 38 | Finish conosle code for users
2016-10-23 | 0.5 | 57 | Finish presentation
2016-10-24 | 0.5 | 40 | Finish Prep
2016-10-24 | 0.75 | 41 | Give presentation
2016-11-05 | 1 | 71
2016-11-07 | 1 | 71
2016-11-08 | 2 | 71
2016-11-11 | 4 | 71
2016-11-13 | 2 | 71
2016-11-19 | 1.5 | 71
2016-11-20 | 1.5 | 71

## Phase 1 Tasks
Task Name | Status | Acitivty ID | Portfolio | Estimate | To Do | Effort | Progress
Spin Up | Done | 1 | Misc | 5 | 0 | 6 | 100%
Set Up Vision Doc | Done | 2 | Vision Document | 1 | 0 | 0.5 | 100%
Set Up Project Plan | Done | 3 | Project Plan | 1 | 0 | 0.5 | 100%
Set Up SQA Plan | Done | 4 | SQA Plan | 1 | 0 | 0.5 | 100%
Make Power Point Slides | Done | 5 | Presentation | 1 | 0 | 1 | 100%
Prep for Presentation | Done | 6 | Presentation | 1 | 0 | 1 | 100%
Set up project | Done | 7 | Prototype | 2 | 0 | 0.5 | 100%
Write Intro | Done | 8 | Vision Document | 2 | 0 | 2 | 100%
Write Project Overview | Done | 9 | Vision Document | 2 | 0 | 1.5 | 100%
Write Critical Uses Cases | Done | 10 | Vision Document | 4 | 0 | 3 | 100%
Write Assumptions, Constraints, Environment | Done | 11 | Vision Document | 1 | 0 | 0.5 | 100%
Write Intro | Done | 12 | Project Plan | 0.5 | 0 | 0.5 | 100%
Write WBS | Done | 13 | Project Plan | 3 | 0 | 1.5 | 100%
Write Cost Estimates | Done | 14 | Project Plan | 1 | 0 | 1.5 | 100%
Write Architect Elab Plan | Done | 15 | Project Plan | 1 | 0 | 0.5 | 100%
Finish SQA Plan | Done | 16 | SQA Plan | 3 | 0 | 1.5 | 100%
Null | Done | 17 |  | 0 | 0 | 0
Create Gantt Chart | Done | 18 | Project Plan | 2 | 0 | 1.5 | 100%
Research platform/environment | Done | 19 | Misc | 2 | 0 | 2 | 100%
Research Servers and API's | Done | 20 | Misc | 2 | 0 | 1 | 100%
Create Receiver | Done | 21 | Prototype | 2 | 0 | 2 | 100%
Create Test Sender | Done | 22 | Prototype | 2 | 0 | 2 | 100%
Research Encryption | Done | 23 | Misc | 2 | 0 | 2 | 100%
Proof of Concept RSA Python | Done | 24 | Prototype | 2 | 0 | 2 | 100%
Give Presentation | Done | 25 | Presentation | 1 | 0 | 1 | 100%
Proof of Concept RSA Java | Done | 26 | Prototype | 3 | 0 | 3.5 | 100%
Encrypted Communication Proof of Concept | Done | 27 | Prototype | 3 | 0 | 3 | 100%
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192

## Phase 1 Portfolio
Portfolio | Total Done | Total To Do | Progress | Phase Done | Phase To Do | Phase Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Misc | 11 | 0 | 100% | 42.5 | 0 | 100% | 2016-06-06 | 2016-11-21 | 2016-07-29 | 168 | 0 | 100% | 0% | 0
Vision Document | 7.5 | 0 | 100%
Project Plan | 6 | 0 | 100%
SQA Plan | 2 | 0 | 100%
Presentation | 3 | 0 | 100%
Prototype | 13 | 0 | 100%

## Phase 2 Tasks
Task Name | Status | Acitivty ID | Portfolio | Estimate | To Do | Effort | Progress
Prep work | Done | 30 | Misc | 1 | 0 | 1 | 100%
Revise Vision Document | Done | 31 | Vision Document | 3 | 0 | 0.5 | 100%
Revise Project Plan | Done | 32 | Project Plan | 3 | 0 | 0.5 | 100%
Set Up Constraints | Done | 33 | Formal Specification | 1 | 0 | 1.5 | 100%
|  | 34 |  | 0 | 0 | 0
Prep for Test Plan | Done | 35 | Test Plan | 0.5 | 0 | 0.5 | 100%
|  | 36 |  |  |  | 0
Perform Inspection | Pending | 37 | Technical Inspection | 0 | 0 | 0
Create Prototype | Done | 38 | Prototype | 8 | 0 | 10 | 100%
|  | 39 |  |  |  | 0
Prep for Presentation | Done | 40 | Presentation | 0.5 | 0 | 0.5 | 100%
Give presentation | In Progress | 41 | Presentation | 1 | 0 | 0.75 | 100%
Set Up Formal Spec | Done | 42 | Formal Specification | 1 | 0 | 1 | 100%
Set Up Classes | Done | 43 | Formal Specification | 2 | 0 | 1.5 | 100%
Set Up Associations | Done | 44 | Formal Specification | 1 | 0 | 0.5 | 100%
Set Up Architectural Design | Done | 45 | Architectural Design | 0.5 | 0 | 0.5 | 100%
Finish Section 2 | Done | 46 | Architectural Design | 1.5 | 0 | 2.5 | 100%
Finish Section 3 | Done | 47 | Architectural Design | 1 | 0 | 1 | 100%
Finish Section 4 | Done | 48 | Architectural Design | 1 | 0 | 2 | 100%
Finish Section 5 | Done | 49 | Architectural Design | 1 | 0 | 0
Finish Section 1 | Done | 50 | Architectural Design | 0.25 | 0 | 0.25 | 100%
Set Up Document | Done | 51 | Test Plan | 0.5 | 0 | 0.5 | 100%
Finish Sections 1 - 8 | Done | 52 | Test Plan | 1 | 0 | 1.5 | 100%
Finish Section 9-11 | Done | 53 | Test Plan | 2 | 0 | 1 | 100%
Set Up Document | Done | 54 | Technical Inspection | 0.5 | 0 | 0.25 | 100%
Finish Document | Done | 55 | Technical Inspection | 1 | 0 | 0.5 | 100%
Set Up Presentation | Done | 56 | Presentation | 0.5 | 0 | 0.25 | 100%
Finish Presentation | Done | 57 | Presentation | 1 | 0 | 2 | 100%
|  | 58 |  |  |  | 0
|  | 59 |  |  |  | 0
|  | 60 |  |  |  | 0
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221

## Phase 2 Portfolio
Portfolio | Total Done | Total To Do | Progress | Phase Done | Phase To Do | Phase Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Misc | 1 | 0 | 100% | 30.5 | 0 | 100% | 2016-08-22 | 2016-11-21 | 2016-10-24 | 91 | -28 | 144.4% | -44.44% | -28
Vision Document | 0.5 | 0 | 100%
Project Plan | 0.5 | 0 | 100%
Formal Specification | 4.5 | 0 | 100%
Architectural Design | 6.25 | 0 | 100%
Test Plan | 3.5 | 0 | 100%
Technical Inspection | 0.75 | 0 | 100%
Prototype | 10 | 0 | 100%
Presentation | 3.5 | 0 | 100%

## Phase 3 Tasks
Task Name | Status | Acitivty ID | Portfolio | Estimate | To Do | Effort | Progress
Component Design |  | 70 | Component Design | 4 | 4 | 0 | 0%
Develop Code | In Progress | 71 | Code | 10 | 2 | 13 | 86.67%
Peform Unit Testing |  | 72 | Testing | 4 | 4 | 0 | 0%
Peform Integration Testing |  | 73 | Testing | 4 | 4 | 0 | 0%
Write User Manual |  | 74 | User Manual | 3 | 3 | 0 | 0%
Project Evaluation |  | 75 | Evaluation | 1 | 1 | 0 | 0%
Create Presentation |  | 76 | Presentation | 2 | 2 | 0 | 0%
Prep for Presentation |  | 77 | Presentation | 1 | 1 | 0 | 0%
Give Presentation |  | 78 | Presentation | 1 | 1 | 0 | 0%
|  | 79 |  |  |  | 0
|  | 80 |  |  |  | 0
|  | 81 |  |  |  | 0
|  | 82 |  |  |  | 0
|  | 83 |  |  |  | 0
|  | 84 |  |  |  | 0
|  | 85 |  |  |  | 0
|  | 86 |  |  |  | 0
|  | 87 |  |  |  | 0
|  | 88 |  |  |  | 0
|  | 89 |  |  |  | 0
|  | 90 |  |  |  | 0
|  | 91 |  |  |  | 0
|  | 92 |  |  |  | 0
|  | 93 |  |  |  | 0
|  | 94 |  |  |  | 0
|  | 95 |  |  |  | 0
|  | 96 |  |  |  | 0
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261

## Phase 3 Portfolio
Portfolio | Total Done | Total To Do | Progress | Phase Done | Phase To Do | Phase Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Misc | 0 | 0 |  | 13 | 22 | 37.14% | 2016-10-24 | 2016-11-21 | 2016-12-09 | 28 | 18 | 60.87% | -23.73% | -10.9143
Component Design | 0 | 4 | 0%
Code | 13 | 2 | 86.67%
Testing | 0 | 8 | 0%
User Manual | 0 | 3 | 0%
Evaluation | 0 | 1 | 0%
Presentation | 0 | 4 | 0%

## Project Overview
Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  |  | Start Date | Todays Date | End Date | Days In | Days Break | Days Left | Class Completed | Delta | Delta Days
Done | To Do | Progress | Done | To Do | Progress | Done | To Do | Progress | 2016-06-06 | 2016-11-21 | 2016-12-09 | 168 | 25 | 18 | 88.82% | -9.19% | -14.7963
42.5 | 0 | 100% | 30.5 | 0 | 100% | 13 | 22 | 37.14%
All Phases
|  |  | Done | To Do | Progress
|  |  | 86 | 22 | 79.63%