## Time Log
Date | Hours | Activity ID | Comments | Phase 1 Hours Total | Phase 2 Hours Total | Phase3 Hours Total | Hours Total | Phase 1 Total | Phase 2 Total | Phase 3 Total | Total Total
2016-06-09 | 1 | 1 |  | 1 | 0 | 0 | 1 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-13 | 2 | 1 |  | 3 | 0 | 0 | 3 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-18 | 2 | 1 |  | 5 | 0 | 0 | 5 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-18 | 1 | 1 | Set Up GitHub | 6 | 0 | 0 | 6 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-18 | 0.5 | 2 |  | 6.5 | 0 | 0 | 6.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-19 | 0.5 | 8 | Intro Paragraph | 7 | 0 | 0 | 7 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-19 | 0.5 | 8 | Motivation and start terms | 7.5 | 0 | 0 | 7.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-19 | 1 | 19 | Look at raspberry pi's and supported languages | 8.5 | 0 | 0 | 8.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-20 | 1 | 20 | Researched web servers and API's | 9.5 | 0 | 0 | 9.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-20 | 0.5 | 8 | Chose terms, formated definitions, made refrences | 10 | 0 | 0 | 10 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-20 | 0.5 | 8 | Finished defining terms | 10.5 | 0 | 0 | 10.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-21 | 0.5 | 9 | Created figure and did overview intro paragraph | 11 | 0 | 0 | 11 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-25 | 1 | 9 | Create system context diagram and write supporting paragraph | 12 | 0 | 0 | 12 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-25 | 0.5 | 10 | Started Use Case Diagram | 12.5 | 0 | 0 | 12.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-25 | 1.5 | 10 | Finished use case diagram and set up use case sections | 14 | 0 | 0 | 14 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-26 | 1 | 10 | Finish Use Case details | 15 | 0 | 0 | 15 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-26 | 0.5 | 11 | Finishe last sections of Vision document | 15.5 | 0 | 0 | 15.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-27 | 0.5 | 3 | Finished project plan setup | 16 | 0 | 0 | 16 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-27 | 0.5 | 12 | Finish Intro | 16.5 | 0 | 0 | 16.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-06-27 | 1 | 18 | Finished most of gantt chart, still needs review of details | 17.5 | 0 | 0 | 17.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-02 | 0.5 | 18 | Finalize Gantt chart and put in document | 18 | 0 | 0 | 18 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-02 | 1.5 | 13 | Finished WBS section | 19.5 | 0 | 0 | 19.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-02 | 0.5 | 14 | Researched COCOMO | 20 | 0 | 0 | 20 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-03 | 1 | 14 | Finished Cost estimate | 21 | 0 | 0 | 21 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-03 | 0.5 | 15 | Finished elab plan | 21.5 | 0 | 0 | 21.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-03 | 0.5 | 4 | Set up SQA document | 22 | 0 | 0 | 22 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-07 | 1 | 19 | Set up Raspberry PI | 23 | 0 | 0 | 23 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-09 | 1.5 | 16 | Finished document | 24.5 | 0 | 0 | 24.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-12 | 0.5 | 7 | Set up environements and started projects | 25 | 0 | 0 | 25 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-12 | 0.5 | 21 | Started Receiver | 25.5 | 0 | 0 | 25.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-12 | 0.5 | 22 | Started Sender | 26 | 0 | 0 | 26 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-14 | 0.5 | 21 |  | 26.5 | 0 | 0 | 26.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-14 | 0.5 | 22 |  | 27 | 0 | 0 | 27 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-23 | 1 | 21 |  | 28 | 0 | 0 | 28 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-23 | 1 | 22 |  | 29 | 0 | 0 | 29 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-24 | 2 | 23 |  | 31 | 0 | 0 | 31 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-26 | 2 | 24 |  | 33 | 0 | 0 | 33 | 42.5 | 30.5 | 41.5 | 114.5
2016-07-31 | 1.5 | 26 | Set up encryption classes | 34.5 | 0 | 0 | 34.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-08-13 | 2 | 26 | Set up sign/verify in java | 36.5 | 0 | 0 | 36.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-08-22 | 1 | 30 | Evaluated schedule/made adjustments | 36.5 | 1 | 0 | 37.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-08-28 | 1 | 5 | Make presentation | 37.5 | 1 | 0 | 38.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-08-30 | 1 | 27 | Play with encryption | 38.5 | 1 | 0 | 39.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-08-31 | 2 | 27 | Final encryption tweaks for demo | 40.5 | 1 | 0 | 41.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-01 | 1 | 6 |  | 41.5 | 1 | 0 | 42.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-01 | 1 | 25 |  | 42.5 | 1 | 0 | 43.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-05 | 0.5 | 31 | Email about feedback | 42.5 | 1.5 | 0 | 44 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-13 | 0.5 | 32 | Review Possilbe Revisions | 42.5 | 2 | 0 | 44.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-13 | 1 | 42 | Set up and look at Use | 42.5 | 3 | 0 | 45.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-18 | 1 | 43 | Working on Classes | 42.5 | 4 | 0 | 46.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-19 | 0.5 | 43 | Finishing up classes | 42.5 | 4.5 | 0 | 47 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-19 | 0.5 | 44 | Finish Associations | 42.5 | 5 | 0 | 47.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-19 | 0.5 | 33 | Decide on Constraints | 42.5 | 5.5 | 0 | 48 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-20 | 1 | 33 | Finish Constraints | 42.5 | 6.5 | 0 | 49 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-20 | 0.5 | 45 | Set up document | 42.5 | 7 | 0 | 49.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-24 | 0.25 | 50 |  | 42.5 | 7.25 | 0 | 49.75 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-24 | 1.5 | 46 | Finished component diagram and interface specification | 42.5 | 8.75 | 0 | 51.25 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-25 | 1 | 46 | Finish section 2 | 42.5 | 9.75 | 0 | 52.25 | 42.5 | 30.5 | 41.5 | 114.5
2016-09-25 | 1 | 47 |  | 42.5 | 10.75 | 0 | 53.25 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-03 | 2 | 48 | Finish Document | 42.5 | 12.75 | 0 | 55.25 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-03 | 0.5 | 35 | Review Test plan document structure | 42.5 | 13.25 | 0 | 55.75 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-04 | 0.5 | 51 | Finish Set UP | 42.5 | 13.75 | 0 | 56.25 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-10 | 1.5 | 52 | Finish sections 1-8 | 42.5 | 15.25 | 0 | 57.75 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-11 | 1 | 53 | Finished document | 42.5 | 16.25 | 0 | 58.75 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-16 | 0.25 | 54 | Finished document set up | 42.5 | 16.5 | 0 | 59 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-16 | 0.5 | 55 | Finish Document | 42.5 | 17 | 0 | 59.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-18 | 0.25 | 56 | Finished setup/prep | 42.5 | 17.25 | 0 | 59.75 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-18 | 1.5 | 57 | Creating Presentation | 42.5 | 18.75 | 0 | 61.25 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-21 | 2 | 38 | Studied up on classes and modules, build user classes | 42.5 | 20.75 | 0 | 63.25 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-22 | 2 | 38 | Setting up console control flow | 42.5 | 22.75 | 0 | 65.25 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-23 | 6 | 38 | Finish conosle code for users | 42.5 | 28.75 | 0 | 71.25 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-23 | 0.5 | 57 | Finish presentation | 42.5 | 29.25 | 0 | 71.75 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-24 | 0.5 | 40 | Finish Prep | 42.5 | 29.75 | 0 | 72.25 | 42.5 | 30.5 | 41.5 | 114.5
2016-10-24 | 0.75 | 41 | Give presentation | 42.5 | 30.5 | 0 | 73 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-05 | 1 | 71 |  | 42.5 | 30.5 | 1 | 74 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-07 | 1 | 71 |  | 42.5 | 30.5 | 2 | 75 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-08 | 2 | 71 |  | 42.5 | 30.5 | 4 | 77 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-11 | 4 | 71 |  | 42.5 | 30.5 | 8 | 81 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-13 | 2 | 71 |  | 42.5 | 30.5 | 10 | 83 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-19 | 1.5 | 71 |  | 42.5 | 30.5 | 11.5 | 84.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-20 | 1.5 | 71 |  | 42.5 | 30.5 | 13 | 86 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-21 | 1 | 71 |  | 42.5 | 30.5 | 14 | 87 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-23 | 2 | 79 | Prep and send out inspection and review Blakes | 42.5 | 30.5 | 16 | 89 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-23 | 3 | 70 | Finish Document | 42.5 | 30.5 | 19 | 92 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-24 | 0.5 | 81 |  | 42.5 | 30.5 | 19.5 | 92.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-25 | 0.5 | 82 |  | 42.5 | 30.5 | 20 | 93 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-25 | 0.5 | 83 |  | 42.5 | 30.5 | 20.5 | 93.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-28 | 2 | 71 |  | 42.5 | 30.5 | 22.5 | 95.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-11-30 | 1.5 | 71 |  | 42.5 | 30.5 | 24 | 97 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-01 | 1 | 71 |  | 42.5 | 30.5 | 25 | 98 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-03 | 3 | 71 |  | 42.5 | 30.5 | 28 | 101 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-07 | 1.5 | 74 |  | 42.5 | 30.5 | 29.5 | 102.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-07 | 1.5 | 84 |  | 42.5 | 30.5 | 31 | 104 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-08 | 0.5 | 80 |  | 42.5 | 30.5 | 31.5 | 104.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-10 | 2 | 72 |  | 42.5 | 30.5 | 33.5 | 106.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-10 | 1 | 80 |  | 42.5 | 30.5 | 34.5 | 107.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-10 | 2 | 75 |  | 42.5 | 30.5 | 36.5 | 109.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-11 | 1 | 79 |  | 42.5 | 30.5 | 37.5 | 110.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-11 | 2 | 76 |  | 42.5 | 30.5 | 39.5 | 112.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-11 | 1 | 77 |  | 42.5 | 30.5 | 40.5 | 113.5 | 42.5 | 30.5 | 41.5 | 114.5
2016-12-12 | 1 | 78 |  | 42.5 | 30.5 | 41.5 | 114.5 | 42.5 | 30.5 | 41.5 | 114.5
|  |  |  | 42.5 | 30.5 | 41.5 | 114.5 | 42.5 | 30.5 | 41.5 | 114.5
|  |  |  | 42.5 | 30.5 | 41.5 | 114.5 | 42.5 | 30.5 | 41.5 | 114.5

## Phase 1 Tasks
Task Name | Status | Acitivty ID | Portfolio | Estimate | To Do | Effort | Progress
Spin Up | Done | 1 | Misc | 5 | 0 | 6 | 100%
Set Up Vision Doc | Done | 2 | Vision Document | 1 | 0 | 0.5 | 100%
Set Up Project Plan | Done | 3 | Project Plan | 1 | 0 | 0.5 | 100%
Set Up SQA Plan | Done | 4 | SQA Plan | 1 | 0 | 0.5 | 100%
Make Power Point Slides | Done | 5 | Presentation | 1 | 0 | 1 | 100%
Prep for Presentation | Done | 6 | Presentation | 1 | 0 | 1 | 100%
Set up project | Done | 7 | Prototype | 2 | 0 | 0.5 | 100%
Write Intro | Done | 8 | Vision Document | 2 | 0 | 2 | 100%
Write Project Overview | Done | 9 | Vision Document | 2 | 0 | 1.5 | 100%
Write Critical Uses Cases | Done | 10 | Vision Document | 4 | 0 | 3 | 100%
Write Assumptions, Constraints, Environment | Done | 11 | Vision Document | 1 | 0 | 0.5 | 100%
Write Intro | Done | 12 | Project Plan | 0.5 | 0 | 0.5 | 100%
Write WBS | Done | 13 | Project Plan | 3 | 0 | 1.5 | 100%
Write Cost Estimates | Done | 14 | Project Plan | 1 | 0 | 1.5 | 100%
Write Architect Elab Plan | Done | 15 | Project Plan | 1 | 0 | 0.5 | 100%
Finish SQA Plan | Done | 16 | SQA Plan | 3 | 0 | 1.5 | 100%
Null | Done | 17 |  | 0 | 0 | 0
Create Gantt Chart | Done | 18 | Project Plan | 2 | 0 | 1.5 | 100%
Research platform/environment | Done | 19 | Misc | 2 | 0 | 2 | 100%
Research Servers and API's | Done | 20 | Misc | 2 | 0 | 1 | 100%
Create Receiver | Done | 21 | Prototype | 2 | 0 | 2 | 100%
Create Test Sender | Done | 22 | Prototype | 2 | 0 | 2 | 100%
Research Encryption | Done | 23 | Misc | 2 | 0 | 2 | 100%
Proof of Concept RSA Python | Done | 24 | Prototype | 2 | 0 | 2 | 100%
Give Presentation | Done | 25 | Presentation | 1 | 0 | 1 | 100%
Proof of Concept RSA Java | Done | 26 | Prototype | 3 | 0 | 3.5 | 100%
Encrypted Communication Proof of Concept | Done | 27 | Prototype | 3 | 0 | 3 | 100%
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192

## Phase 1 Portfolio
Portfolio | Total Done | Total To Do | Progress | Phase Done | Phase To Do | Phase Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Misc | 11 | 0 | 100% | 42.5 | 0 | 100% | 2016-06-06 | 2016-12-11 | 2016-07-29 | 188 | 0 | 100% | 0% | 0
Vision Document | 7.5 | 0 | 100%
Project Plan | 6 | 0 | 100%
SQA Plan | 2 | 0 | 100%
Presentation | 3 | 0 | 100%
Prototype | 13 | 0 | 100%

## Phase 2 Tasks
Task Name | Status | Acitivty ID | Portfolio | Estimate | To Do | Effort | Progress
Prep work | Done | 30 | Misc | 1 | 0 | 1 | 100%
Revise Vision Document | Done | 31 | Vision Document | 3 | 0 | 0.5 | 100%
Revise Project Plan | Done | 32 | Project Plan | 3 | 0 | 0.5 | 100%
Set Up Constraints | Done | 33 | Formal Specification | 1 | 0 | 1.5 | 100%
|  | 34 |  | 0 | 0 | 0
Prep for Test Plan | Done | 35 | Test Plan | 0.5 | 0 | 0.5 | 100%
|  | 36 |  |  |  | 0
Perform Inspection | Pending | 37 | Technical Inspection | 0 | 0 | 0
Create Prototype | Done | 38 | Prototype | 8 | 0 | 10 | 100%
|  | 39 |  |  |  | 0
Prep for Presentation | Done | 40 | Presentation | 0.5 | 0 | 0.5 | 100%
Give presentation | In Progress | 41 | Presentation | 1 | 0 | 0.75 | 100%
Set Up Formal Spec | Done | 42 | Formal Specification | 1 | 0 | 1 | 100%
Set Up Classes | Done | 43 | Formal Specification | 2 | 0 | 1.5 | 100%
Set Up Associations | Done | 44 | Formal Specification | 1 | 0 | 0.5 | 100%
Set Up Architectural Design | Done | 45 | Architectural Design | 0.5 | 0 | 0.5 | 100%
Finish Section 2 | Done | 46 | Architectural Design | 1.5 | 0 | 2.5 | 100%
Finish Section 3 | Done | 47 | Architectural Design | 1 | 0 | 1 | 100%
Finish Section 4 | Done | 48 | Architectural Design | 1 | 0 | 2 | 100%
Finish Section 5 | Done | 49 | Architectural Design | 1 | 0 | 0
Finish Section 1 | Done | 50 | Architectural Design | 0.25 | 0 | 0.25 | 100%
Set Up Document | Done | 51 | Test Plan | 0.5 | 0 | 0.5 | 100%
Finish Sections 1 - 8 | Done | 52 | Test Plan | 1 | 0 | 1.5 | 100%
Finish Section 9-11 | Done | 53 | Test Plan | 2 | 0 | 1 | 100%
Set Up Document | Done | 54 | Technical Inspection | 0.5 | 0 | 0.25 | 100%
Finish Document | Done | 55 | Technical Inspection | 1 | 0 | 0.5 | 100%
Set Up Presentation | Done | 56 | Presentation | 0.5 | 0 | 0.25 | 100%
Finish Presentation | Done | 57 | Presentation | 1 | 0 | 2 | 100%
|  | 58 |  |  |  | 0
|  | 59 |  |  |  | 0
|  | 60 |  |  |  | 0
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221

## Phase 2 Portfolio
Portfolio | Total Done | Total To Do | Progress | Phase Done | Phase To Do | Phase Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Misc | 1 | 0 | 100% | 30.5 | 0 | 100% | 2016-08-22 | 2016-12-11 | 2016-10-24 | 111 | -48 | 176.2% | -76.19% | -48
Vision Document | 0.5 | 0 | 100%
Project Plan | 0.5 | 0 | 100%
Formal Specification | 4.5 | 0 | 100%
Architectural Design | 6.25 | 0 | 100%
Test Plan | 3.5 | 0 | 100%
Technical Inspection | 0.75 | 0 | 100%
Prototype | 10 | 0 | 100%
Presentation | 3.5 | 0 | 100%

## Phase 3 Tasks
Task Name | Status | Acitivty ID | Portfolio | Estimate | To Do | Effort | Progress
Component Design | Done | 70 | Component Design | 4 | 0 | 3 | 100%
Develop Code | In Progress | 71 | Code | 12 | 0 | 21.5 | 100%
Peform Testing | Done | 72 | Testing | 2 | 0 | 2 | 100%
|  | 73 |  | 0 | 0 | 0
Finish User Manual | Done | 74 | User Manual | 1 | 0 | 1.5 | 100%
Finish Evaluation | Done | 75 | Evaluation | 1 | 0 | 2 | 100%
Create Presentation | Done | 76 | Presentation | 2 | 0 | 2 | 100%
Prep for Presentation | Done | 77 | Presentation | 1 | 0 | 1 | 100%
Give Presentation | Done | 78 | Presentation | 1 | 0 | 1 | 100%
Get techinical Inspection completed | Done | 79 | Technical Inspection | 3 | 0 | 3 | 100%
Finish Assesment | Done | 80 | Assesment Evaluation | 1 | 0 | 1.5 | 100%
Set Up User Manual | Done | 81 | User Manual | 1 | 0 | 0.5 | 100%
Set Up Project Evaluation | Done | 82 | Evaluation | 1 | 0 | 0.5 | 100%
Set Up Assesment Evaluation | Done | 83 | Assesment Evaluation | 1 | 0 | 0.5 | 100%
Write API | Done | 84 | User Manual | 1 | 0 | 1.5 | 100%
|  | 85 |  |  |  | 0
|  | 86 |  |  |  | 0
|  | 87 |  |  |  | 0
|  | 88 |  |  |  | 0
|  | 89 |  |  |  | 0
|  | 90 |  |  |  | 0
|  | 91 |  |  |  | 0
|  | 92 |  |  |  | 0
|  | 93 |  |  |  | 0
|  | 94 |  |  |  | 0
|  | 95 |  |  |  | 0
|  | 96 |  |  |  | 0
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261

## Phase 3 Portfolio
Portfolio | Total Done | Total To Do | Progress | Phase Done | Phase To Do | Phase Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Misc | 0 | 0 |  | 41.5 | 0 | 100% | 2016-10-24 | 2016-12-11 | 2016-12-12 | 48 | 1 | 97.96% | 2.041% | 1
Component Design | 3 | 0 | 100%
Code | 21.5 | 0 | 100%
Testing | 2 | 0 | 100%
User Manual | 3.5 | 0 | 100%
Evaluation | 2.5 | 0 | 100%
Presentation | 4 | 0 | 100%
Technical Inspection | 3 | 0 | 100%
Assesment Evaluation | 2 | 0 | 100%

## Project Overview
Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  |  | Start Date | Todays Date | End Date | Days In | Days Break | Days Left | Class Completed | Delta | Delta Days
Done | To Do | Progress | Done | To Do | Progress | Done | To Do | Progress | 2016-06-06 | 2016-12-11 | 2016-12-12 | 188 | 25 | 1 | 99.39% | 0.6098% | 1
42.5 | 0 | 100% | 30.5 | 0 | 100% | 41.5 | 0 | 100%
All Phases
|  |  | Done | To Do | Progress | [11 empty] | Phase | Percent
|  |  | 114.5 | 0 | 100% | [11 empty] | Phase 1 | 37.12%
[17 empty] | Phase 2 | 26.64%
[17 empty] | Phase 3 | 36.24%
[17 empty] | Phase | Estimation Accuracy
[17 empty] | Phase 1 | 118.8%
[17 empty] | Phase 2 | 110.7%
[17 empty] | Phase 3 | 77.11%