## Time Log
Date | Hours | Activity ID | Comments
2016-06-09 | 1 | 1
2016-06-13 | 2 | 1
2016-06-18 | 2 | 1
2016-06-18 | 1 | 1 | Set Up GitHub
2016-06-18 | 0.5 | 2
2016-06-19 | 0.5 | 8 | Intro Paragraph
2016-06-19 | 0.5 | 8 | Motivation and start terms
2016-06-19 | 1 | 19 | Look at raspberry pi's and supported languages
2016-06-20 | 1 | 20 | Researched web servers and API's
2016-06-20 | 0.5 | 8 | Chose terms, formated definitions, made refrences
2016-06-20 | 0.5 | 8 | Finished defining terms
2016-06-21 | 0.5 | 9 | Created figure and did overview intro paragraph
2016-06-25 | 1 | 9 | Create system context diagram and write supporting paragraph
2016-06-25 | 0.5 | 10 | Started Use Case Diagram
2016-06-25 | 1.5 | 10 | Finished use case diagram and set up use case sections
2016-06-26 | 1 | 10 | Finish Use Case details
2016-06-26 | 0.5 | 11 | Finishe last sections of Vision document
2016-06-27 | 0.5 | 3 | Finished project plan setup
2016-06-27 | 0.5 | 12 | Finish Intro
2016-06-27 | 1 | 18 | Finished most of gantt chart, still needs review of details
2016-07-02 | 0.5 | 18 | Finalize Gantt chart and put in document
2016-07-02 | 1.5 | 13 | Finished WBS section
2016-07-02 | 0.5 | 14 | Researched COCOMO
2016-07-03 | 1 | 14 | Finished Cost estimate
2016-07-03 | 0.5 | 15 | Finished elab plan
2016-07-03 | 0.5 | 4 | Set up SQA document

## Phase 1 Tasks
Task Name | Status | Acitivty ID | Portfolio | Estimate | To Do | Effort | Progress
Spin Up | Done | 1 | Misc | 5 | 0 | 6 | 100%
Set Up Vision Doc | Done | 2 | Vision Document | 1 | 0 | 0.5 | 100%
Set Up Project Plan | Done | 3 | Project Plan | 1 | 0 | 0.5 | 100%
Set Up SQA Plan | Done | 4 | SQA Plan | 1 | 0 | 0.5 | 100%
Make Power Point Slides |  | 5 | Presentation | 4 | 4 | 0 | 0%
Prep for Presentation |  | 6 | Presentation | 2 | 2 | 0 | 0%
Set up project |  | 7 | Prototype | 3 | 3 | 0 | 0%
Write Intro | Done | 8 | Vision Document | 2 | 0 | 2 | 100%
Write Project Overview | Done | 9 | Vision Document | 2 | 0 | 1.5 | 100%
Write Critical Uses Cases | Done | 10 | Vision Document | 4 | 0 | 3 | 100%
Write Assumptions, Constraints, Environment | Done | 11 | Vision Document | 1 | 0 | 0.5 | 100%
Write Intro | Done | 12 | Project Plan | 0.5 | 0 | 0.5 | 100%
Write WBS | Done | 13 | Project Plan | 3 | 0 | 1.5 | 100%
Write Cost Estimates | Done | 14 | Project Plan | 1 | 0 | 1.5 | 100%
Write Architect Elab Plan | Done | 15 | Project Plan | 1 | 0 | 0.5 | 100%
Finish SQA Plan | In Progress | 16 | SQA Plan | 3 | 3 | 0 | 0%
Finish Prototype |  | 17 | Prototype | 15 | 15 | 0 | 0%
Create Gantt Chart | Done | 18 | Project Plan | 2 | 0 | 1.5 | 100%
Research platform/environment | In Progress | 19 | Misc | 2 | 1 | 1 | 50%
Research Servers and API's | In Progress | 20 | Misc | 2 | 1 | 1 | 50%
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192

## Phase 1 Portfolio
Portfolio | Total Done | Total To Do | Progress | Phase Done | Phase To Do | Phase Progress | Start Date | Today | End Date | Days In | Days Left | Class Completed | Delta | Delta Days
Misc | 8 | 2 | 80% | 22 | 29 | 43.14% | 2016-06-06 | 2016-07-03 | 2016-07-29 | 27 | 26 | 50.94% | -7.806% | -4.1373
Vision Document | 7.5 | 0 | 100%
Project Plan | 6 | 0 | 100%
SQA Plan | 0.5 | 3 | 14.29%
Presentation | 0 | 6 | 0%
Prototype | 0 | 18 | 0%